## Cover
Project Challenge 2
Team 1
Level Up
| Team Member : | 1 | Min Khant
|  | 2 | Myo Thiha
|  | 3 | Swun Htet Oo
|  | 4 | Yab Naing Htwe
|  | 5 | Zin Min Htet
|  | 6 | Phyo Thiha
|  |  |  | Create Date | 2022-06-28
Update Date

## Customer Requirement
Customer Requirement (要件定義) | Level Up | [6 empty] | Create Date | 2022-06-28
[8 empty] | Update Date | 2022-07-08 19:42
Customer Requirement
1.Student
|  | 1 | Login/Logout
|  | 2 | Register | (email,fb,twitter)
|  | 3 | Search (DD-> categories,keywords,instructor) Fliter => popular,best seller,Free,paid,rating,new
|  | 4 | My Course (pin)
|  | 5 | Cart,Checkout(Card)
|  | 6 | Channel(one time rating,multi comment on videol),QA,Report on Channel, Add Note on live
Script,Add Quiz(pop up,calculate),Lecture note Download),Time ,Level
|  | 7 | By Instructor or center (one to many) => Profile)
|  | 8 | By Categories,By keyword (Channel)
|  | 9 | home page (darkmode),leaner count,buy count,active user count)
|  | 10 | fav list
|  | 11 | notification ( wishlist,new channel,promotion,update on my channel)
|  | 12 | My Porfile
|  | 13 | Contact Us
|  | 14 | Services
|  | 15 | Privacy policy
|  | 16 | Guides
|  | 17 | Apply instructor (image,exp,age,contact,project link)
| 1.2.1 Admin (SA) |  |  |  | 1.2.2 Admin(AD)
|  | 1 | Login/Logout |  |  | 1 | Login/Logout
|  | 2 | Channel(List,Delete) |  |  | 2 | Channel(List,Add,Update),(script(add,update,delete)
|  | 3 | Request Instructor list (Approve,Denied)= |  |  |  | Lecture note upload
|  |  | >generate ID & Password |  |  | 3 | Status by Channel (look,subscribe)
|  | 4 | Instrcutor List(Bann,unBan) |  |  | 4 | Community by Channel (rating,comment,QA,
|  | 5 | All Channel (look,subscribe) |  |  |  | reply,ranking by quiz
|  | 6 | Community by Channel (rating,comment,QA, |  |  | 5 | Profile
|  | 7 | reply,ranking by quiz |  |  | 6 | Report Student to SA
|  | 8 | Setting |  |  | 7 | Appeal to SA
- Register
- Contact (CRUD)
- Service (CRUD)
- Privacy Policy(CRUD)
- Guide (CRUD)
|  | 9 | Search (Instructor,Channel)
filter => viewer,subscriber
|  | 10 | Report Student List
(Waning noti,ban comment,disable account by day,ignore)

## Schedule
Schedule (進捗） |  | Level Up | [9 empty] | Create Date
Update Date
No | Sub | Task | Assign | Est Start | Est End | Duration Day | Act Start | Act End | Act Duration | Work Done
1 |  | Schedule（進捗） | ALL | 2022-06-28 | 2022-07-28 | 30 | 2022-06-28 |  | -44740 | 0%
2 |  | Project Flow（流れ） | YN,ST | 2022-07-03 | 2022-07-05 | 2 |  |  | 0 | 0%
3 |  | Screen Design（画面設計） | ALL | 2022-07-01 | 2022-07-14 | 13 | 2022-07-04 |  | -44746 | 32.19%
| 1 | Header | MK | 2022-07-05 | 2022-07-06 | 1 | 2022-07-04 | 2022-07-06 | 2 | 90%
| 2 | Footer | MK | 2022-07-05 | 2022-07-06 | 1 | 2022-07-04 | 2022-07-06 | 2 | 90%
| 3 | Sign In | MTH | 2022-07-05 | 2022-07-06 | 1 | 2022-07-05 |  | -44747 | 85%
| 4 | Registration | MTH | 2022-07-06 | 2022-07-07 | 1 | 2022-07-06 |  | -44748 | 85%
| 5 | Dashboard | PTH | 2022-07-05 | 2022-07-08 | 3 | 2022-07-05 | 2022-07-08 | 3 | 90%
| 6 | Cart | MK | 2022-07-06 | 2022-07-07 | 1 | 2022-07-06 |  | -44748 | 85%
| 7 | My Course | MK | 2022-07-07 | 2022-07-08 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 8 | Instuctor List | SHO | 2022-07-05 | 2022-07-06 | 1 | 2022-07-05 | 2022-07-06 | 1 | 90%
| 9 | Instuctor Detail | SHO | 2022-07-05 | 2022-07-06 | 1 | 2022-07-05 |  | -44747 | 60%
| 10 | Course List | YN | 2022-07-05 | 2022-07-07 | 2 | 2022-07-05 | 2022-07-07 | 2 | 90%
| 11 | Course Detail | YN | 2022-07-05 | 2022-07-07 | 2 | 2022-07-05 | 2022-07-07 | 2 | 90%
| 12 | Checkout | ZMT | 2022-07-06 | 2022-07-07 | 1 | 2022-07-05 |  | -44747 | 85%
| 13 | Payment | ZMT | 2022-07-07 | 2022-07-08 | 1 | 2022-07-07 |  | -44749 | 85%
| 14 | Video | SHO | 2022-07-06 | 2022-07-08 | 2 | 2022-07-06 | 2022-07-08 | 2 | 90%
| 15 | Quiz Popup | MK | 2022-07-08 | 2022-07-09 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 16 | Profile | PTH | 2022-07-05 | 2022-07-08 | 3 | 2022-07-05 | 2022-07-07 | 2 | 90%
| 17 | Edit Profile | PTH | 2022-07-05 | 2022-07-08 | 3 | 2022-07-05 | 2022-07-07 | 2 | 90%
| 18 | Favourite | ZMT | 2022-07-08 | 2022-07-09 | 1 |  |  | 0 | 0% | Move to Dashboard
| 19 | Notification | ZMT | 2022-07-08 | 2022-07-09 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 20 | Guide | MTH | 2022-07-07 | 2022-07-08 | 1 | 2022-07-07 |  | -44749 | 85%
| 21 | Contact | MTH | 2022-07-08 | 2022-07-09 | 1 |  |  | 0 | 0%
| 22 | Service | MTH | 2022-07-09 | 2022-07-10 | 1 |  |  | 0 | 0%
| 23 | Terms/Policy | ZMT | 2022-07-09 | 2022-07-10 | 1 |  |  | 0 | 0%
| 24 | About Us | ZMT | 2022-07-09 | 2022-07-10 | 1 | 2022-07-06 | 2022-07-07 | 1 | 90%
| 25 | Home Page | MK | 2022-07-09 | 2022-07-10 | 1 | 2022-07-04 | 2022-07-06 | 2 | 90%
| 26 | Apply Instructor | [6 empty] | 0 | 0%
| 27 | Login | YN | 2022-07-07 | 2022-07-08 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 28 | Dashboard | YN | 2022-07-07 | 2022-07-08 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 29 | IN:Profile ( Edit mode) | YN | 2022-07-08 | 2022-07-09 | 1 |  |  | 0 | 0%
| 30 | IN:Edit Profile | YN | 2022-07-08 | 2022-07-09 | 1 | 2022-07-06 |  | -44748 | 50%
| 31 | IN:Course List | YN | 2022-07-09 | 2022-07-10 | 1 |  |  | 0 | 0%
| 32 | IN:Course Upload | YN | 2022-07-09 | 2022-07-10 | 1 |  |  | 0 | 0%
| 33 | IN:Course Edit | YN | 2022-07-09 | 2022-07-10 | 1 |  |  | 0 | 0%
| 34 | IN:Appeal | MTH | 2022-07-10 | 2022-07-11 | 1 |  |  | 0 | 0%
| 35 | IN:Community(Rate & Review) | MTH | 2022-07-10 | 2022-07-11 | 1 |  |  | 0 | 0%
| 36 | IN:Video List | SHO | 2022-07-08 | 2022-07-09 | 1 |  |  | 0 | 0%
| 37 | IN:Video Upload | SHO | 2022-07-09 | 2022-07-10 | 1 |  |  | 0 | 0%
| 38 | IN:Video Info | SHO | 2022-07-10 | 2022-07-11 | 1 |  |  | 0 | 0%
| 39 | IN:Edit Video | SHO | 2022-07-09 | 2022-07-10 | 1 |  |  | 0 | 0%
| 40 | IN:Quizz List | MK | 2022-07-10 | 2022-07-11 | 1 |  |  | 0 | 0%
| 41 | IN:Quiz Update | MK | 2022-07-10 | 2022-07-11 | 1 |  |  | 0 | 0%
| 42 | IN:Quiz View | MK | 2022-07-10 | 2022-07-11 | 1 |  |  | 0 | 0%
| 43 | IN:Script Update | MK | 2022-07-11 | 2022-07-12 | 1 |  |  | 0 | 0%
| 44 | IN:Order List | SSS | [5 empty] | 0 | 0%
| 45 | IN:Orde Detail | SSS | [5 empty] | 0 | 0%
| 46 | AD: Review Appeal | MTH | 2022-07-11 | 2022-07-12 | 1 |  |  | 0 | 0%
| 47 | AD: Instructor List | PTH | 2022-07-08 | 2022-07-09 | 1 |  |  | 0 | 0%
| 48 | AD:Profile ( View mode) | PTH | 2022-07-09 | 2022-07-10 | 1 |  |  | 0 | 0%
| 49 | AD:Course List | SSS |  |  | 0 |  |  | 0 | 0%
| 50 | AD:Course Detail | SSS |  |  | 0 |  |  | 0 | 0%
| 51 | AD:Video List | SSS |  |  | 0 |  |  | 0 | 0%
| 52 | AD:Video View | SSS |  |  | 0 |  |  | 0 | 0%
| 53 | AD:Request Instuctor List | MTH | 2022-07-11 | 2022-07-12 | 1 |  |  | 0 | 0%
| 54 | AD:Review Instuctor | MTH | 2022-07-11 | 2022-07-12 | 1 |  |  | 0 | 0%
| 55 | AD:Admin List | SSS |  |  | 0 |  |  | 0 | 0%
| 56 | AD:Admin Add | SSS |  |  | 0 |  |  | 0 | 0%
| 57 | AD:Admin Update | SSS |  |  | 0 |  |  | 0 | 0%
| 58 | AD:Contact | ZMT | 2022-07-10 | 2022-07-11 | 1 |  |  | 0 | 0%
| 59 | AD:Services | ZMT | 2022-07-10 | 2022-07-11 | 1 |  |  | 0 | 0%
| 60 | AD:Privacy Policy | ZMT | 2022-07-11 | 2022-07-12 | 1 |  |  | 0 | 0%
| 61 | AD:Guide | ZMT | 2022-07-11 | 2022-07-12 | 1 |  |  | 0 | 0%
| 62 | AD:About Us | ZMT | 2022-07-12 | 2022-07-13 | 1 |  |  | 0 | 0%
| 63 | AD:Order List | SSS | [5 empty] | 0 | 0%
| 64 | AD:Orde Detail | SSS | [5 empty] | 0 | 0%
4 |  | Database（DB設計書） |  | 2022-07-06 | 2022-07-11 | 5 |  |  | 0 | 0%
5 |  | Development（開発） |  |  |  | 0 |  |  | 0 | 0%
| 1 | Header |  |  |  | 0 |  |  | 0 | 0%
| 2 | Footer |  |  |  | 0 |  |  | 0 | 0%
| 3 | Sign In |  |  |  | 0 |  |  | 0 | 0%
| 4 | Registration |  |  |  | 0 |  |  | 0 | 0%
| 5 | Dashboard |  |  |  | 0 |  |  | 0 | 0%
| 6 | Cart |  |  |  | 0 |  |  | 0 | 0%
| 7 | My Course |  |  |  | 0 |  |  | 0 | 0%
| 8 | Instuctor List |  |  |  | 0 |  |  | 0 | 0%
| 9 | Instuctor Detail |  |  |  | 0 |  |  | 0 | 0%
| 10 | Course List |  |  |  | 0 |  |  | 0 | 0%
| 11 | Course Detail |  |  |  | 0 |  |  | 0 | 0%
| 12 | Checkout |  |  |  | 0 |  |  | 0 | 0%
| 13 | Payment |  |  |  | 0 |  |  | 0 | 0%
| 14 | Video |  |  |  | 0 |  |  | 0 | 0%
| 15 | Quiz Popup |  |  |  | 0 |  |  | 0 | 0%
| 16 | Profile |  |  |  | 0 |  |  | 0 | 0%
| 17 | Edit Profile |  |  |  | 0 |  |  | 0 | 0%
| 18 | Favourite |  |  |  | 0 |  |  | 0 | 0% | Move to Dashboard
| 19 | Notification |  |  |  | 0 |  |  | 0 | 0%
| 20 | Guide |  |  |  | 0 |  |  | 0 | 0%
| 21 | Contact |  |  |  | 0 |  |  | 0 | 0%
| 22 | Service |  |  |  | 0 |  |  | 0 | 0%
| 23 | Terms/Policy |  |  |  | 0 |  |  | 0 | 0%
| 24 | About Us |  |  |  | 0 |  |  | 0 | 0%
| 25 | Home Page |  |  |  | 0 |  |  | 0 | 0%
| 26 | Apply Instructor | [6 empty] | 0 | 0%
| 27 | Login |  |  |  | 0 |  |  | 0 | 0%
| 28 | Dashboard |  |  |  | 0 |  |  | 0 | 0%
| 29 | IN:Profile ( Edit mode) |  |  |  | 0 |  |  | 0 | 0%
| 30 | IN:Edit Profile |  |  |  | 0 |  |  | 0 | 0%
| 31 | IN:Course List |  |  |  | 0 |  |  | 0 | 0%
| 32 | IN:Course Upload |  |  |  | 0 |  |  | 0 | 0%
| 33 | IN:Course Edit |  |  |  | 0 |  |  | 0 | 0%
| 34 | IN:Appeal |  |  |  | 0 |  |  | 0 | 0%
| 35 | IN:Community(Rate & Review) |  |  |  | 0 |  |  | 0 | 0%
| 36 | IN:Video List |  |  |  | 0 |  |  | 0 | 0%
| 37 | IN:Video Upload |  |  |  | 0 |  |  | 0 | 0%
| 38 | IN:Video Info |  |  |  | 0 |  |  | 0 | 0%
| 39 | IN:Edit Video |  |  |  | 0 |  |  | 0 | 0%
| 40 | IN:Quizz List |  |  |  | 0 |  |  | 0 | 0%
| 41 | IN:Quiz Update |  |  |  | 0 |  |  | 0 | 0%
| 42 | IN:Quiz View |  |  |  | 0 |  |  | 0 | 0%
| 43 | IN:Script Update |  |  |  | 0 |  |  | 0 | 0%
| 44 | IN:Order List | [6 empty] | 0 | 0%
| 45 | IN:Orde Detail | [6 empty] | 0 | 0%
| 46 | AD: Review Appeal |  |  |  | 0 |  |  | 0 | 0%
| 47 | AD: Instructor List |  |  |  | 0 |  |  | 0 | 0%
| 48 | AD:Profile ( View mode) |  |  |  | 0 |  |  | 0 | 0%
| 49 | AD:Course List |  |  |  | 0 |  |  | 0 | 0%
| 50 | AD:Course Detail |  |  |  | 0 |  |  | 0 | 0%
| 51 | AD:Video List |  |  |  | 0 |  |  | 0 | 0%
| 52 | AD:Video View |  |  |  | 0 |  |  | 0 | 0%
| 53 | AD:Request Instuctor List |  |  |  | 0 |  |  | 0 | 0%
| 54 | AD:Review Instuctor |  |  |  | 0 |  |  | 0 | 0%
| 55 | AD:Admin List |  |  |  | 0 |  |  | 0 | 0%
| 56 | AD:Admin Add |  |  |  | 0 |  |  | 0 | 0%
| 57 | AD:Admin Update |  |  |  | 0 |  |  | 0 | 0%
| 58 | AD:Contact |  |  |  | 0 |  |  | 0 | 0%
| 59 | AD:Services |  |  |  | 0 |  |  | 0 | 0%
| 60 | AD:Privacy Policy |  |  |  | 0 |  |  | 0 | 0%
| 61 | AD:Guide |  |  |  | 0 |  |  | 0 | 0%
| 62 | AD:About Us |  |  |  | 0 |  |  | 0 | 0%
| 63 | AD:Order List |  |  |  | 0 |  |  | 0 | 0%
| 64 | AD:Orde Detail |  |  |  | 0 |  |  | 0 | 0%
6 |  | Unit Test（単体試験） |  |  |  | 0 |  |  | 0 | 0%
7 |  | Integration Test（結合試験） |  |  |  | 0 |  |  | 0 | 0%
111
[5 empty] | Month | 3.7

## Screen Flow
Main Flow (プロジャック流れ） |  | Level Up |  | Create Date
Update Date
Explanation of Project
プロジャックの説明
(プロジャック流れ）
| Path： |  | Path：

## Screen Design
Screen Design (画面設計） | Level Up | Create Date
Update Date
Screen Name ：

## DB Design
DB Design (DB設計） |  | Level Up | [8 empty] | Create Date
Update Date
DB Name ：
Table Name ：
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Assign
1 | Design | 2 | Document | 3 | Database
| Min Khant |  | Swun Htet Oo |  | Phyo Thiha | Schedule
| Myo Thiha |  | Yan Naing Htwe |  | Zin Min Htet
4 | Vimeo | 5 | Design Component
| Swun Htet Oo |  | Yan Naing Htwe
DEV
| Min Khant |  | Swun Htet Oo |  | Phyo Thiha
| Myo Thiha |  | Yan Naing Htwe |  | Zin Min Htet