## Cover
Project Challenge 2
Team 1
Level Up
| Team Member : | 1 | Min Khant
|  | 2 | Myo Thiha
|  | 3 | Swun Htet Oo
|  | 4 | Yab Naing Htwe
|  | 5 | Zin Min Htet
|  | 6 | Phyo Thiha
|  |  |  | Create Date | 2022-06-28
Update Date

## Customer Requirement
Customer Requirement (要件定義) | Level Up | [6 empty] | Create Date | 2022-06-28
[8 empty] | Update Date | 2022-07-27 11:45
Customer Requirement
1.Student
|  | 1 | Login/Logout
|  | 2 | Register | (email,fb,twitter)
|  | 3 | Search (DD-> categories,keywords,instructor) Fliter => popular,best seller,Free,paid,rating,new
|  | 4 | My Course (pin)
|  | 5 | Cart,Checkout(Card)
|  | 6 | Channel(one time rating,multi comment on videol),QA,Report on Channel, Add Note on live
Script,Add Quiz(pop up,calculate),Lecture note Download),Time ,Level
|  | 7 | By Instructor or center (one to many) => Profile)
|  | 8 | By Categories,By keyword (Channel)
|  | 9 | home page (darkmode),leaner count,buy count,active user count)
|  | 10 | fav list
|  | 11 | notification ( wishlist,new channel,promotion,update on my channel)
|  | 12 | My Porfile
|  | 13 | Contact Us
|  | 14 | Services
|  | 15 | Privacy policy
|  | 16 | Guides
|  | 17 | Apply instructor (image,exp,age,contact,project link)
| 1.2.1 Admin (SA) |  |  |  | 1.2.2 Admin(AD)
|  | 1 | Login/Logout |  |  | 1 | Login/Logout
|  | 2 | Channel(List,Delete) |  |  | 2 | Channel(List,Add,Update),(script(add,update,delete)
|  | 3 | Request Instructor list (Approve,Denied)= |  |  |  | Lecture note upload
|  |  | >generate ID & Password |  |  | 3 | Status by Channel (look,subscribe)
|  | 4 | Instrcutor List(Bann,unBan) |  |  | 4 | Community by Channel (rating,comment,QA,
|  | 5 | All Channel (look,subscribe) |  |  |  | reply,ranking by quiz
|  | 6 | Community by Channel (rating,comment,QA, |  |  | 5 | Profile
|  | 7 | reply,ranking by quiz |  |  | 6 | Report Student to SA
|  | 8 | Setting |  |  | 7 | Appeal to SA
- Register
- Contact (CRUD)
- Service (CRUD)
- Privacy Policy(CRUD)
- Guide (CRUD)
|  | 9 | Search (Instructor,Channel)
filter => viewer,subscriber
|  | 10 | Report Student List
(Waning noti,ban comment,disable account by day,ignore)

## Schedule
Schedule (進捗） |  | Level Up | [9 empty] | Create Date
Update Date
No | Sub | Task | Assign | Est Start | Est End | Duration Day | Act Start | Act End | Act Duration | Work Done
1 |  | Schedule（進捗） | ALL | 2022-06-28 | 2022-08-05 | 38 | 2022-06-28 |  | -44740 | 0%
2 |  | Project Flow（流れ） | YN,ST | 2022-07-03 | 2022-07-05 | 2 |  |  | 0 | 0%
3 |  | Screen Design（画面設計） | ALL | 2022-07-01 | 2022-07-14 | 13 | 2022-07-04 |  | -44746 | 90%
| 1 | Header | MK | 2022-07-05 | 2022-07-06 | 1 | 2022-07-04 | 2022-07-06 | 2 | 90%
| 2 | Footer | MK | 2022-07-05 | 2022-07-06 | 1 | 2022-07-04 | 2022-07-06 | 2 | 90%
| 3 | Sign In | MTH | 2022-07-05 | 2022-07-06 | 1 | 2022-07-05 | 2022-07-06 | 1 | 90%
| 4 | Registration | MTH | 2022-07-06 | 2022-07-07 | 1 | 2022-07-06 | 2022-07-06 | 0 | 90%
| 5 | Forget Password | MTH | 2022-07-06 | 2022-07-07 | 1 | 2022-07-06 | 2022-07-06 | 0 | 90%
| 6 | Dashboard | PTH | 2022-07-05 | 2022-07-08 | 3 | 2022-07-05 | 2022-07-08 | 3 | 90%
| 7 | Cart | MK | 2022-07-06 | 2022-07-07 | 1 | 2022-07-06 | 2022-07-07 | 1 | 90%
| 8 | Instuctor List | SHO | 2022-07-05 | 2022-07-06 | 1 | 2022-07-05 | 2022-07-06 | 1 | 90%
| 9 | Instuctor Detail | SHO | 2022-07-05 | 2022-07-06 | 1 | 2022-07-05 | 2022-07-06 | 1 | 90%
| 10 | Course List | YN | 2022-07-05 | 2022-07-07 | 2 | 2022-07-05 | 2022-07-07 | 2 | 90%
| 11 | Course Detail | YN | 2022-07-05 | 2022-07-07 | 2 | 2022-07-05 | 2022-07-07 | 2 | 90%
| 12 | Checkout | ZMT | 2022-07-06 | 2022-07-07 | 1 | 2022-07-05 | 2022-07-07 | 2 | 90%
| 13 | Payment | ZMT | 2022-07-07 | 2022-07-08 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 14 | Video | SHO | 2022-07-06 | 2022-07-08 | 2 | 2022-07-06 | 2022-07-08 | 2 | 90%
| 15 | Quiz Popup | MK | 2022-07-08 | 2022-07-09 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 16 | Edit Profile | PTH | 2022-07-05 | 2022-07-08 | 3 | 2022-07-05 | 2022-07-07 | 2 | 90%
| 17 | Notification | ZMT | 2022-07-08 | 2022-07-09 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 18 | Guide | MTH | 2022-07-07 | 2022-07-08 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 19 | Contact | MTH | 2022-07-08 | 2022-07-09 | 1 | 2022-07-08 | 2022-07-09 | 1 | 90%
| 20 | Service | MTH | 2022-07-09 | 2022-07-10 | 1 | 2022-07-08 | 2022-07-09 | 1 | 90%
| 21 | Terms/Policy | ZMT | 2022-07-09 | 2022-07-10 | 1 | 2022-07-09 | 2022-07-10 | 1 | 90%
| 22 | About Us | ZMT | 2022-07-09 | 2022-07-10 | 1 | 2022-07-06 | 2022-07-07 | 1 | 90%
| 23 | Home Page | MK | 2022-07-09 | 2022-07-10 | 1 | 2022-07-04 | 2022-07-06 | 2 | 90%
| 24 | Apply Instructor | MK | 2022-07-09 | 2022-07-10 | 1 | 2022-07-09 | 2022-07-10 | 1 | 90%
| 25 | Login | YN | 2022-07-07 | 2022-07-08 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 26 | Forget Password | MTH | 2022-07-06 | 2022-07-07 | 1 | 2022-07-06 | 2022-07-06 | 0 | 90%
| 27 | Dashboard | YN | 2022-07-07 | 2022-07-08 | 1 | 2022-07-07 | 2022-07-08 | 1 | 90%
| 28 | IN:Profile ( Edit mode) | YN | 2022-07-08 | 2022-07-09 | 1 | 2022-07-08 | 2022-07-09 | 1 | 90%
| 29 | IN:Edit Profile | YN | 2022-07-08 | 2022-07-09 | 1 | 2022-07-06 | 2022-07-09 | 3 | 90%
| 30 | IN:Course List | YN | 2022-07-09 | 2022-07-10 | 1 | 2022-07-09 | 2022-07-10 | 1 | 90%
| 31 | IN:Course Upload | YN | 2022-07-09 | 2022-07-10 | 1 | 2022-07-09 | 2022-07-10 | 1 | 90%
| 32 | IN:Course Edit | YN | 2022-07-09 | 2022-07-10 | 1 | 2022-07-09 | 2022-07-10 | 1 | 90%
| 33 | IN:Appeal | MTH | 2022-07-10 | 2022-07-11 | 1 | 2022-07-10 | 2022-07-11 | 1 | 90%
| 34 | IN:Community(Rate & Review) | MTH | 2022-07-10 | 2022-07-11 | 1 | 2022-07-10 | 2022-07-11 | 1 | 90%
| 35 | IN:Order List | MK | 2022-07-10 | 2022-07-11 | 1 | 2022-07-10 | 2022-07-11 | 1 | 90%
| 36 | AD: Review Appeal List | MTH | 2022-07-11 | 2022-07-12 | 1 | 2022-07-11 | 2022-07-12 | 1 | 90%
| 37 | AD: Review Appeal | MTH | 2022-07-11 | 2022-07-12 | 1 | 2022-07-11 | 2022-07-12 | 1 | 90%
| 38 | AD: Instructor List | PTH | 2022-07-08 | 2022-07-09 | 1 | 2022-07-08 | 2022-07-09 | 1 | 90%
| 39 | AD:Profile ( View mode) | PTH | 2022-07-09 | 2022-07-10 | 1 | 2022-07-08 | 2022-07-09 | 1 | 90% | Remarks: Someone did it.already completed
| 40 | AD:Course List | YN | 2022-07-09 | 2022-07-10 | 1 | 2022-07-09 | 2022-07-10 | 1 | 90%
| 41 | AD:Course View | YN | 2022-07-09 | 2022-07-10 | 1 | 2022-07-09 | 2022-07-10 | 1 | 90%
| 42 | AD:Request Instuctor List | MTH | 2022-07-11 | 2022-07-12 | 1 | 2022-07-11 | 2022-07-12 | 1 | 90%
| 43 | AD:Review Instuctor | MTH | 2022-07-11 | 2022-07-12 | 1 | 2022-07-11 | 2022-07-12 | 1 | 90%
| 44 | AD:Admin List | MK | 2022-07-11 | 2022-07-12 | 1 | 2022-07-11 | 2022-07-12 | 1 | 90%
| 45 | AD:Admin Add | MK | 2022-07-11 | 2022-07-12 | 1 | 2022-07-11 | 2022-07-12 | 1 | 90%
| 46 | AD:Admin Update | MK | 2022-07-11 | 2022-07-12 | 1 | 2022-07-11 | 2022-07-12 | 1 | 90%
| 47 | AD:Contact | ZMT | 2022-07-10 | 2022-07-11 | 1 | 2022-07-11 | 2022-07-12 | 1 | 90%
| 48 | AD:Services | ZMT | 2022-07-10 | 2022-07-11 | 1 | 2022-07-10 | 2022-07-11 | 1 | 90%
| 49 | AD:Privacy Policy | ZMT | 2022-07-11 | 2022-07-12 | 1 | 2022-07-11 | 2022-07-12 | 1 | 90%
| 50 | AD:Guide | ZMT | 2022-07-11 | 2022-07-12 | 1 | 2022-07-11 | 2022-07-12 | 1 | 90%
| 51 | AD:About Us | ZMT | 2022-07-12 | 2022-07-13 | 1 | 2022-07-12 | 2022-07-13 | 1 | 90%
| 52 | AD:Order List | MK | 2022-07-10 | 2022-07-11 | 1 | 2022-07-10 | 2022-07-11 | 1 | 90%
4 |  | Database（DB設計書） |  | 2022-07-06 | 2022-07-11 | 5 | 2022-07-15 | 2022-07-17 | 2 | 100%
5 |  | Development（開発） |  | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 49.72%
| 1 | Header | MK | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 80% | 0.5
| 2 | Footer | MK | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 80% | 0.5
| 3 | Sign In | PTH | 2022-07-15 | 2022-07-28 | 13 | 2022-07-18 | 2022-07-19 | 1 | 80% | 1
| 4 | Registration | PTH | 2022-07-15 | 2022-07-28 | 13 | 2022-07-18 | 2022-07-19 | 1 | 80% | 1
| 5 | Forget Password | MTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 55% | 1.5
| 6 | Dashboard | PTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 1
| 7 | Cart | MK | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 55% | 1
| 8 | Instuctor List | SHO | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 90%
| 9 | Instuctor Detail | SHO | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 90%
| 10 | Course List | YN | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50%
| 11 | Course Detail | YN | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50%
| 12 | Checkout | ZMT | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 2
| 13 | Payment | ZMT | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 1.5
| 14 | Video | SHO | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 90%
| 15 | Quiz Popup | MK | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 1
| 16 | Edit Profile | PTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 1
| 17 | Notification | ZMT | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 1.5
| 18 | Guide | MTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 1.5
| 19 | Contact | MTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | Alert 1
| 20 | Service | MTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 1.5
| 21 | Terms/Policy | ZMT | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 85% | 0
| 22 | About Us | ZMT | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 0.5
| 23 | Home Page | MK | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 2
| 24 | Apply Instructor | MK | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 1
| 25 | Login | PTH | 2022-07-15 | 2022-07-28 | 13 | 2022-07-18 | 2022-07-19 | 1 | 90% | 1
| 26 | Dashboard | MK | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 10% | 3
| 27 | Forget Password | MTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 20% | 1
| 28 | IN:Profile ( Edit mode) | PTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 60% | 2
| 29 | IN:Edit Profile | PTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 60% | 0
| 30 | IN:Course List | YN | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 40%
| 31 | IN:Course Upload | YN | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 40%
| 32 | IN:Course Edit | YN | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 40%
| 33 | IN:Appeal | ZMT | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 1
| 34 | IN:Community(Rate & Review) | SHO | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 40% | 1.5
| 35 | IN:Order List | SHO | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 40% | 1.5
| 36 | AD: Review Appeal List | MTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 0% | 1
| 37 | AD: Review Appeal | PTH | 2022-07-15 | 2022-07-28 | 13 | 2022-07-18 | 2022-07-19 | 1 | 90% | 1
| 38 | AD: Instructor List | ZMT | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 50% | 1.5
| 39 | AD:Profile ( View mode) | SHO | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 0% | Remarks: Someone did it.already completed
| 40 | AD:Course List | YN | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 40%
| 41 | AD:Course View | YN | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 40%
| 42 | AD:Request Instuctor List | SHO | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 0% | 1
| 43 | AD:Review Instuctor | SHO | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 0% | 1
| 44 | AD:Admin List | MK | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 90% | 0
| 45 | AD:Admin Add | MK | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 90% | 0
| 46 | AD:Admin Update | MK | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 90% | 0
| 47 | AD:Contact | MTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 0% | 1.5
| 48 | AD:Services | MTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 0% | 1
| 49 | AD:Privacy Policy | ZMT | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 90% | 0
| 50 | AD:Guide | MTH | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 0% | 1
| 51 | AD:About Us | ZMT | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 80% | 0.5
| 52 | AD:Order List | SHO | 2022-07-15 | 2022-07-28 | 13 |  |  | 0 | 0% | 1
6 |  | Unit Test（単体試験） |  |  |  | 0 |  |  | 0 | 0%
7 |  | Integration Test（結合試験） |  |  |  | 0 |  |  | 0 | 0%
806
[5 empty] | Month | 26.8667

## Screen Flow
Main Flow (プロジャック流れ） |  | Level Up |  | Create Date
Update Date
Explanation of Project
プロジャックの説明
(プロジャック流れ）
| Path： |  | Path：
Login Page
Login
Roll
Login fail?
Instructor
Admin
Instructor
Dashboard
Profile
Course List
Appeal to Admin
Log Out
Edit Profile
Course Edit
Course Upload
Rate/Review
Video List
Video Edit
Video Info
Script
Video Upload
Info Update
Quizz List
Script Update
Quizz Update
Quizz View
Order List
Order Details
Dashboard
Review Appeal
Instructor's list
Course list
Request Instructor list
Admin list
Order List
Log Out
Settings
Approve
Unban
Add Banlist
Profile
Course List
Course Detail
Instructor
Video List
Ban
Video Delete
Video View
Course Delete
Review Instructor
Approve
Deny
Add Instructor List
Admin Update
Admin Add
Order Detail
Rate/Review
Admin
App Master
Site Master
Servies
About Us
Contact
Guide
Privacy Policy

## Screen Design
Screen Design (画面設計） | Level Up | Create Date
Update Date
Screen Name ：

## Code Rule
Code Rule |  | Food_Lab |  | Create Date | 2021-12-25
|  |  |  | Update Date | 2022-07-27 11:45
Global Rule
|  | 1 | Camel Naming Rule for all Function
|  | 2 | Max Code line: 170 line in one method
|  | 3 | Max Argument : 7 parameter in one function
|  | 4 | ALL Capatial Letter for global variable
|  | 5 | Variable name must be meaningful (Not allow x,y,x,I,etc…)
|  | 6 | Must write comment in every method (header)
/*
*Create:Author Name(Date)
*Update:Author Name(Date)
*Explanation of method or function
*Parameter: explain
*Return
*/
|  | 7 | Not allow 3 time nested Loop Condition
|  | 8 | If using recursive method,must have break condition
|  | 9 | Must be format.
HTML Rule
|  | 1 | Must write close tag
|  | 2 | Must write comment for open close tag
|  | 3 | Not allow inline css and internal css
|  | 4 | ID must be unique in one html
CSS Rule
|  | 1 | Use scale unit (em,%,vh,vw) instead of px.(As much as possible)
|  | 2 | Use root declear for common properties.
|  | 3 | Must write comment by block
|  | 4 | Not allow minus assign (Example : margin : -10px)
|  | 5 | Must be responsive
Javascript/Jquery Rule
|  | 1 | Global varible must be write in start of line
|  | 2 | If webpage is used jquery,Must be write (document.ready…)
|  | 3 | Avoid Deadcode
Json Rule
|  | 1 | Key must be meaningful
Ajax Rule
|  | 1 | Must have ContectType,success,error catch and statuscode control
|  | 2 | Must have timeout properties
|  | 3 | ID must be encrypt
Laravel
|  | 1 | Log must be divided by Category
| Php | 2 | Must use try catch in complex business logic
|  | 3 | Must use lang
|  | 4 | Password must be encrypt
| Php | 5 | Class name Must be Pascal Naming Rule
| Php | 6 | View name Must be Camel Naming Rue
| Php | 7 | Avoid Deadcode
|  | 8 | Must MVC Rule
|  | 9 | Must be divided Validation Class
| Php | 10 | Class Inside Oncall function must be private
|  | 11 | Must delete session if it is not use

## DB Design
DB Design (DB設計） |  | Level Up | [8 empty] | Create Date
Update Date
DB Name ：
Table Name ：
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Assign
1 | Design | 2 | Document | 3 | Database
| Min Khant |  | Swun Htet Oo |  | Phyo Thiha | Schedule
| Myo Thiha |  | Yan Naing Htwe |  | Zin Min Htet
4 | Vimeo | 5 | Design Component
| Swun Htet Oo |  | Yan Naing Htwe
DEV
| Min Khant |  | Swun Htet Oo |  | Phyo Thiha
| Myo Thiha |  | Yan Naing Htwe |  | Zin Min Htet